## Sheet1
Mobile Plan & Audit-Log Planning (Seekers)
Epic | Epic Name | Ticket ID | User Stories | Assigned To | Status | Start Date | End Date | Duration (In day)
1 | Rest API Creation in Spring Boot Application | MP-1 | Read By id Controller | Komal | Done | 2022-08-25 | 2022-08-26 | 2
|  | MP-2 | Update Controller | Satyam | Done | 2022-08-26 | 2022-08-29 | 4
|  | MP-4 | Delete Controller | Shubham | Done | 2022-08-26 | 2022-08-29 | 4
|  | MP-5 | Update & Delete Service | Prathamesh | Done | 2022-08-26 | 2022-08-29 | 4
2 | UI and It's integration with Spring boot Application | MP-6 | Home Webpage & Create Webpage | Shubham | Done | 2022-08-30 | 2022-09-05 | 7
|  | MP-7 | Search Webpage & Update By id Webpage | Prathamesh | Done | 2022-08-30 | 2022-09-05 | 7
|  | MP-8 | Delete Webpage & View All Webpage | Satyam | Done | 2022-09-30 | 2022-09-05 | 7
|  | MP-9 | Integration of Front end & Backend | Prathamesh & Shubham | Done | 2022-09-06 | 2022-09-12 | 7
|  | MP-10 | About Us webpage | Pranjali | Done | 2022-09-06 | 2022-09-12 | 7
3 | Creation and Integration of Audit log with Mobile Plan | MP-11 | Backend Controller | Satyam | Done | 2022-09-13 | 2022-09-16 | 4
|  | MP-12 | Backend Service | prathamesh | Done | 2022-09-13 | 2022-09-16 | 4
|  | MP-13 | UI - View webpage | Pranjali | Done | 2022-09-13 | 2022-09-19 | 7
|  | MP-14 | UI - Search Webpage | Komal | Done | 2022-09-13 | 2022-09-19 | 7
|  | MP-15 | Overall Improvement | Shubham | Done | 2022-09-16 | 2022-09-20 | 2
4 | Documentation & Testcases | MP-16 | Defect(Bug) Report | Pratik | Done | 2022-09-21 | 2022-09-24 | 6
|  | MP-17 | Postman JSON Collection | Pratik | Done | 2022-09-22 | 2022-09-26 | 6
|  | MP-18 | Functional Test Cases & Rest Api Test Cases | pratik | Done | 2022-09-23 | 2022-09-28 | 8